**CONSTRUCTION PROJECT**

Project Overview

* Objective: Construct a residential building.
* Activities: From site preparation to finishing touches.

Activities, Durations, and Dependency

1. A: Site Preparation - 5 days

2. B: Foundation Excavation - 7 days (A)

3. C: Foundation Laying - 3 days (B)

4. D: Structural Framework - 10 days (C)

5. E: Plumbing Installation - 5 days (A)

6. F: Electrical Installation - 7 days (C)

7. G: Roof Construction - 6 days (D)

8. H: Exterior Walls - 8 days (D)

9. I: Interior Walls - 5 days (E,F)

10. J: Windows and Doors Installation - 4 days (G)

11. K: Insulation - 3 days (H)

12. L: Drywall Installation - 5 days (I,J)

13. M: Flooring - 4 days (K)

14. N: Painting - 6 days (L)

15. O: Interior Fixtures - 7 days (M)

16. P: Landscaping - 4 days (N)

17. Q: Final Inspection - 2 days (O)

18. R: Cleanup - 2 days (P)

19. S: Handover - 1 day (R)

20. T: Project Closure - 1 day (S)