## RISK ANALYSIS
RISK ANALYSIS OF 3D SEISMIC DATA ACQUISITION PROJECT
S/N | ACTIVITY | RISK | PROBABILITY | SEVERITY | RISK MATRIX | RISK(%) | LEVEL | RISK MITIGATION | TOP RISK | CONTIGENCY PLAN
1 | SCOUTING | Kidnapping and Hostage taking | 2 | 5 | 10 | 40 | High | Involvement of security personnel and local guard the scouting team. | FIRE OUTBREAK | Initiation of the FIRE Emergency Procedure
2 | Clearing of site | Cutlass cut | 2 | 3 | 6 | 24 | Medium | Use of complete PPE for the task | MAN LOST | Initiation of the MAN LOST Emergency Procedure. This involves contitution of search team lead by the Party Chief.
3 |  | Snake Bite | 3 | 5 | 15 | 60 | Very High | Wear complete PPE | SNAKE BITE | Initiattion of MEDEVAC Emergency Procedures
4 | Sinking of borehole | Injury from Drilling equipments | 2 | 3 | 6 | 24 | Medium | Use complete PPE for the task
|  | Hydrogen Sulphide gas | 1 | 5 | 5 | 20 | Medium | Conduct gas test before work begin, ensure the tester is position close to the drill point
5 | Construction of offices, workshops, and staff accommodation areas | Fire Outbreak | 4 | 5 | 20 | 80 | Extreme | Install Safety Critical Equipment
|  | Slip and fall | 2 | 3 | 6 | 24 | Medium | Use of complete PPE for the task
6 | Installation of 100ft Radio mast | Fall from height | 2 | 5 | 10 | 40 | High | Use of Harness Belt
|  | Suspended load | 1 | 5 | 5 | 20 | Medium | Avoid working under suspeded load
7 | Installations of safety critical equipments | Slip and fall | 1 | 3 | 3 | 12 | Low | Use of complete PPE for the task
|  | Fall from height | 1 | 4 | 4 | 16 | Medium | Use of Harness Belt
8 | Host Communities Permit/Sensitization | Irrate Villagers/Youth | 2 | 4 | 8 | 32 | Medium | Avoid working under suspeded load
|  | Hostage Taking | 2 | 5 | 10 | 40 | High | Apply Irrate villagers/youth attack procedure
Mobilization
9 | Personnel employment | Compromise in the employment process | 2 | 4 | 8 | 32 | Medium | Sticking to the employment requirements and standards.
10 | Medical test | Compromised medical test | 1 | 4 | 4 | 16 | Medium | Use of certified medical profesionals
11 | Swimming test | Compromised Swimming test | 1 | 4 | 4 | 16 | Medium | Swimming test should superviced by the client representatives
12 | Provision of PPE for employee | Sub Standard PPE | 1 | 3 | 3 | 12 | Low | Quality Inspection should be done by client Rep
SURVEY ACTIVITIES
13 | Survey Line cutting | Wildlife and Bee attack | 3 | 4 | 12 | 48 | High | Line trecking prosedures should be followed, Follow the bee attack procedures
|  | Cutlass cut | 1 | 3 | 3 | 12 | Low | Use complete PPE for the task
|  | Slip and fall | 2 | 3 | 6 | 24 | Medium | Use probing stick when necessary and put on complete PPE
|  | Man lost | 4 | 5 | 20 | 80 | Extreme | Follow Line trecking procedure, always follow buddy man system
|  | Drowning | 1 | 5 | 5 | 20 | Medium | Swimming test, use of PFD, follow man overboard procedure when necessary
|  | Snake Bite | 3 | 5 | 15 | 60 | Very High | Follow Line trecking procedure, Wear complete PPE
DRILLING ACTIVITIES
14 | Drilling of short points and Pre-loading | Hydrogen Sulphide Gas | 2 | 5 | 10 | 40 | High | Conduct gas test before work begin, ensure the tester is position close to the drill point
|  | Injury from Drilling equipments | 3 | 3 | 9 | 36 | Medium | Wear complete PPE
|  | Poor Explosives Handling | 2 | 5 | 10 | 40 | High | Retriction of unauthorized personnel
|  | Slip and fall | 3 | 3 | 9 | 36 | Medium | Use Probing stick when necessary and put on complete PPE
|  | Bee attack | 2 | 5 | 10 | 40 | High | Line trecking prosedures should be followed, Follow the bee attack procedures
|  | Transportation of personnel and equipments | 2 | 5 | 10 | 40 | High | Speed limit, always use seat belt, No alcohol or drugs while driving
|  | Explosives Transportation | 2 | 5 | 10 | 40 | High | safe distance of at least 30m from Dynamite vehicle and ditonator vehicle should be maintain
RECORDING ACTIVITIES
15 | Laying of geophones and cables | Irrate Villagers/Youth | 3 | 3 | 9 | 36 | Medium | Apply Irrate villagers/youth attack procedure
|  | Slip and fall | 3 | 3 | 9 | 36 | Medium | Use probing stick when necessary and put on complete PPE
|  | Bee attack | 2 | 5 | 10 | 40 | High | Line trecking prosedures should be followed, Follow the bee attack procedures
|  | Man lost | 4 | 5 | 20 | 80 | Extreme | Follow Line trecking procedure, always follow buddy man system
|  | Transportation of personnel and equipments | 2 | 5 | 10 | 40 | High | Speed limit, always use seat belt, No alcohol or drugs while driving
16 | Data Acquisition | Damage to the environment and man made objects | 1 | 5 | 5 | 20 | Medium | Ensure all shot points are safe for operation and drilled to specification
|  | Cables and Geophone theft by locals | 2 | 4 | 8 | 32 | Medium | Employment of local guard to protect field equipments
|  | Lost of Data or Virus attact | 1 | 5 | 5 | 20 | Medium | All data aquired should be Backed up
|  | Poor Data Quality | 2 | 3 | 6 | 24 | Medium | Real time quality check should carried out
17 | Dispatch of Deliverables | Theft or Lost of Deliverables in the course of delivery to client | 1 | 5 | 5 | 20 | Medium | All Delliverables should be transported by air
18 | Assessment/Compensation of Damages to Host Communities | Irrate Villagers/Youth | 2 | 3 | 6 | 24 | Medium | Apply Irrate villagers/youth attack procedure