## Borehole Drilling Service
Provision of Quality Water For Woji Community
Activity | Indexing List | Description | Predecessor | Duration (days) | Start Date | Finish Date | Resources | Cost ($) | Lag (days)
Community Affairs |  | Engaging with the local community | None | 30 | 2024-06-25 | 2024-07-25 | Community Liaison Officer (CLO) | 500 | 0
| Meeting 1 | Engaging with the local community | None | 10 | 2024-06-25 | 2024-07-04 | Community Liaison Officer (CLO)
| Meeting 2 | Engaging with the local community | Meeting 1 | 10 | 2024-07-05 | 2024-07-14 | Community Liaison Officer (CLO)
| Final Meeting | Engaging with the local community | Meeting 2 | 10 | 2024-07-15 | 2024-07-25 | Community Liaison Officer (CLO)
Site Assessment |  | Community Affairs | None | 2 | 2024-07-27 | 2024-07-29 | Geological Engineer | 1000 | 0
| Initial Consultation | Meeting with client | None | 0 | 2024-07-27 | 2024-07-27 | Geological Engineer | 100 | 0
| Site Reconnaissance | Preliminary site visit | Initial Consultation | 0 | 2024-07-27 | 2024-07-27 | Geological Engineer | 100 | 0
| Historical Data Review | Reviewing geological and hydrological data | Site Reconnaissance | 0 | 2024-07-27 | 2024-07-27 | Geological Engineer | 100 | 0
| Soil Sampling | Collecting soil samples | Historical Data Review | 1 | 2024-07-27 | 2024-07-29 | Geological Engineer, Field Assistant | 300 | 0
| Soil Analysis | Laboratory analysis of soil samples | Soil Sampling | 0 | 2024-07-29 | 2024-07-29 | Geological Engineer, Lab Technician | 200 | 0
| Report Preparation | Compiling site assessment report | Soil Analysis | 0 | 2024-07-29 | 2024-07-29 | Geological Engineer | 100 | 0
| Client Presentation | Presenting report and recommendations to client | Report Preparation | 0 | 2024-07-29 | 2024-07-29 | Geological Engineer | 100 | 0
Geophysical Survey |  | Conducting geophysical survey | Site Assessment | 3 | 2024-07-30 | 2024-08-01 | Geophysicist, Equipment | 3000 | 0
| Pre-Survey Planning | Planning survey layout and selecting methods | None | 0 | 2024-07-30 | 2024-07-30 | Geophysicist | 200 | 0
| Equipment Setup & Calibration | Setting up and calibrating survey equipment | Pre-Survey Planning | 0 | 2024-07-30 | 2024-07-30 | Geophysicist, Field Technician | 300 | 0
| Field Data Acquisition | Collecting geophysical data across the defined grid | Equipment Setup & Calibration | 2 | 2024-07-30 | 2024-07-31 | Geophysicist, Field Technician | 1200 | 0
| Data Processing & Interpretation | Processing and interpreting geophysical data | Field Data Acquisition | 1 | 2024-06-14 | 2024-06-14 | Geophysicist, Data Analyst | 800 | 0
| Report Preparation | Compiling results into a detailed report | Data Processing & Interpretation | 0 | 2024-06-14 | 2024-06-14 | Geophysicist | 300 | 0
| Client Presentation | Presenting the report and recommendations to the client | Report Preparation | 0 | 2024-06-14 | 2024-06-14 | Geophysicist | 200 | 0
Mobilization |  | Mobilizing equipment and team | Geophysical Survey | 2 | 2024-06-15 | 2024-06-16 | Drilling Crew, Trucks | 1500 | 0
Drilling Operations |  | Drilling the borehole | Community Affairs | 10 | 2024-06-19 | 2024-06-28 | Drilling Crew, Rig, Diesel | 25000 | 0
Geological Supervision |  | Supervision during drilling | Drilling Operations | 10 (concurrent) | 2024-06-19 | 2024-06-28 | Geological Engineer | 2000 | -10
Pump Installation |  | Installing water pump | Geological Supervision | 2 | 2024-06-29 | 2024-06-30 | Pump Installation Crew | 5000 | 0
| Pump Site Preparation | Preparing the borehole site for pump installation | None | 0 | 2024-06-29 | 2024-06-29 | Field Technician, Laborers | 300 | 0
| Pump and Equipment Procurement | Procuring the necessary pump and related equipment | Pump Site Preparation | 1 | 2024-06-29 | 2024-06-30 | Procurement Specialist | 3000 | -1
| Installation of Pump | Installing the pump and connecting it to the borehole | Pump and Equipment Procurement | 0 | 2024-06-30 | 2024-06-30 | Pump Installation Specialist, Electrician, Field Technician | 1000 | 0
| Testing and Commissioning | Testing the installed pump for proper functionality | Installation of Pump | 0 | 2024-06-30 | 2024-06-30 | Pump Installation Specialist, Electrician, Field Technician | 700 | 0
Water Testing |  | Testing water quality | Pump Installation | 2 | 2024-07-01 | 2024-07-02 | Water Quality Analyst | 1500 | 0
Demobilization |  | Demobilizing of equipment and team | Geophysical Survey | 2 | 2024-06-15 | 2024-06-16 | Drilling Crew, Trucks | 1000 | 0
Site Cleanup |  | Cleaning up the site | Water Testing | 1 | 2024-07-03 | 2024-07-03 | Cleanup Crew | 500 | 0
| Training and Handover | Training client on pump operation, water testing and maintenance, handover | None | 0 | 2024-07-03 | 2024-07-03 | Pump Installation Specialist | 0 | 0

## Sheet1
TASK |  | RISK | LIKELIHOOD | SEVERITY | RISK MATRIX | PERCENTAGE | CONTINGENCY PLAN
Community Affairs | [7 empty] | Legend
| Meeting 1 | Kidnapping, Political Instability, Health Hazards, Security Risks | 5 | 5 | 25 | 100% | Engage CLO, Security Escort, Hire Vigilante |  | Extreme
| Meeting 2 | [7 empty] | Very high
| Final Meeting | [7 empty] | High
Site Assessment | [8 empty] | Medium
| Initial Consultation | Conflict of Interest | 2 | 2 | 4 | 16% | Consult Community Leaders |  | Low
| Site Reconnaissance | Community Resistance | 3 | 4 | 12 | 48% | Employ Local Workforce |  | Very low
| Historical Data Review | Data Unavailability | 4 | 3 | 12 | 48% | Conduct Ground Truthing
| Soil Sampling | Equipment Malfunction | 2 | 1 | 2 | 8% | Maintain Backup Equipment
| Soil Analysis | Lab Equipment Failure, Data Interpretation Errors | 1 | 2 | 2 | 8% | Perform Regular Calibration and Proofreading
| Report Preparation | Reporting Delays | 2 | 4 | 8 | 32% | Ensure Timely Report Submission
| Client Presentation | Report Errors | 1 | 2 | 2 | 8% | Conduct Thorough Review and Analysis
Geophysical Survey
| Pre-Survey Planning | Incomplete Equipment Inventory | 1 | 2 | 2 | 8% | Perform Detailed Cross-checks
| Equipment Setup & Calibration | Personnel Health and Safety Risks, Improper Handling | 1 | 3 | 3 | 12% | Replace Personnel, Appoint HSE Officer
| Field Data Acquisition | Traverse Line Misalignment | 2 | 4 | 8 | 32% | Utilize Compass Clinometer with Care
| Data Processing & Interpretation | Data Oversight | 1 | 2 | 2 | 8% | Implement Senior Officer Data Review
| Report Preparation | Reporting Delays | 2 | 4 | 8 | 32% | Ensure Timely Report Submission
| Client Presentation | Report Errors | 1 | 2 | 2 | 8% | Conduct Thorough Review and Analysis
Mobilization |  | Funding Delays | 5 | 5 | 25 | 100% | Issue Constant Reminders
Drilling Operations |  | Occupational and Workplace Hazards | 2 | 4 | 8 | 32% | Deploy Onsite HSE Officer
Geological Supervision |  | Lack of Focus | 1 | 2 | 2 | 8% | Assign Additional Geological Engineer
Pump Installation
| Pump Site Preparation | Inadequate Cleaning | 2 | 1 | 2 | 8% | Ensure Proper HSE Officer Supervision
| Pump and Equipment Procurement | Unethical Practices | 2 | 1 | 2 | 8% | Conduct Procurement Oversight
| Installation of Pump | Lack of Focus | 1 | 2 | 2 | 8% | Promote Attention to Detail
| Testing and Commissioning | Power Failures | 1 | 1 | 1 | 4% | Provide Power Backup Systems
Water Testing |  | Procedural Noncompliance | 1 | 1 | 1 | 4% | Emphasize Professional Conduct
Demobilization |  | Accidents, Community Resilience Issues | 2 | 3 | 6 | 24% | Implement Safety Protocols, Community Engagement
Site Cleanup
| Cleaning and Handover | Inadequate Cleaning | 2 | 1 | 2 | 8% | Ensure Proper HSE Officer Supervision